Project Plan - Methodology

Selected Methodology: Agile Development

Introduction :-

Agile Development is a software development methodology that divides a project into small parts that can be developed, tested, and improved incrementally. It emphasizes flexibility, teamwork, communication, and continuous feedback.

Why Agile Was Selected ?

Agile Development was selected for the Meeting Room Booking

System for the following reasons:

1. Flexibility: The team can modify system requirements when necessary.

2. Team Collaboration: The five team members can coordinate their work and share responsibilities.

3. Incremental Development: The system can be developed feature by feature.

4. Continuous Testing: Each feature can be tested before moving to the next stage.

5. Feedback and Improvement: Feedback can help the team improve the system during development.

Applying Agile to the Meeting Room Booking System :-

The project will be divided into the following iterations:

Iteration 1: Requirements Analysis

- Identify the needs of employees and administrators.

- Determine the problems with the current meeting room booking process.

- Define the system requirements.

Iteration 2: System Design

- Design the user interface.

- Design the database for rooms, users, and bookings.

- Define the booking workflow.

Iteration 3: Core System Development

- Display available meeting rooms.

- Allow users to book rooms for specific dates and times.

- Prevent overlapping bookings.

Iteration 4: Additional Features

- Allow users to modify or cancel bookings.

- Enable administrators to manage rooms and reservations.

- Display booking details and confirmation.

Iteration 5: Testing and Evaluation

- Test room availability and reservation functionality.

- Check that booking conflicts are prevented.

- Fix errors and improve the system based on feedback.

Advantages of Agile for Our Project :-

Agile Development allows the team to develop the Meeting Room Booking System incrementally, identify problems early, coordinate responsibilities, and improve features throughout development.

Conclusion :-

Agile Development allows the team to develop the Meeting Room Booking System incrementally, identify problems early, coordinate responsibilities, and improve features throughout development.

Time Estimation

|  | Standard percentages | Estimated time based on planning time |
| --- | --- | --- |
| Planning | 19.05 % | 8 days |
| Analysis | 21.43 % | 9 days |
| Design | 21.43 % | 9 days |
| Implementation & Testing | 57.14 % | 24 days |
| Total | 100 % | 50 days |

Case Study: Business System Implementation

Background:-

- An organization needs an efficient way to manage its meeting rooms and reservations.

- Employees need to book meeting rooms for meetings, discussions, and training sessions.

- The organization plans to implement a Meeting Room Booking System to improve the reservation process.

Problems Identified:-

- Difficulty checking meeting room availability.

- Double booking of the same meeting room.

- Manual booking procedures that waste time.

- Difficulty managing booking modifications and cancellations.

- Lack of centralized booking information.

Project Objectives:-

- Organize all meeting room reservations in one system.

- Allow users to check room availability.

- Prevent overlapping reservations.

- Simplify booking, modification, and cancellation.

- Help administrators manage rooms and reservations.

System Development Plan:-

The project team plans to follow the System Development Life Cycle (SDLC) to analyze, design, develop, test, and implement the Meeting Room Booking System.

Key SDLC Phases:-

1. Planning – Identify project goals, feasibility, resources, and the project schedule.

2. Analysis – Gather user requirements through interviews and questionnaires.

3. Design – Prepare the Data Flow Diagram (DFD), Entity Relationship Diagram (ERD), database design, and user interface.

4. Implementation – Develop the booking system and its main functions.

5. Testing – Test room availability, reservations, and booking conflict prevention.

6. Deployment – Make the system available to users and provide basic instructions.

7. Maintenance – Fix problems and update the system when necessary.

Questions:-

1. Which SDLC methodology is most suitable for developing the Meeting Room Booking System, and why?

2. How can the proposed system solve the identified problems?

Methodology Options:-

1. Waterfall Method

2. Parallel Method

3. Rapid Application Development (RAD)

4. Iterative Method

5. Agile Development

| Name | System Request |
| --- | --- |
| ID | 1 |
| Start Date | 18 / 10 / 2026 |
| End Date | 19 / 10 /2026 |
| Person Assigned | Project Manger |
| Priority | High |
| Resources Needed | Client Brief |
| Estimated Time | 2 Days |
| Actual Time | Not Stated |
| Predecessors | None |
| Slack | 0 Days |

Project Identifications

| Name | Feasibility Study |
| --- | --- |
| ID | 2 |
| Start Date | 20 / 10 / 2026 |
| End Date | 23 / 10 /2026 |
| Person Assigned | Business Analysis |
| Priority | High |
| Resources Needed | Cost Sheet |
| Estimated Time | 4 Days |
| Actual Time | Not Stated |
| Predecessors | 1 |
| Slack | 0 Days |

| Name | Project Plan (Gantt-Chart) |
| --- | --- |
| ID | 3 |
| Start Date | 24 / 10 / 2026 |
| End Date | 26 / 10 /2026 |
| Person Assigned | Project Manger |
| Priority | Medium |
| Resources Needed | MS Project |
| Estimated Time | 3 Days |
| Actual Time | Not Stated |
| Predecessors | 2 |
| Slack | 0 Days |

| Name | Risk Assesment |
| --- | --- |
| ID | 4 |
| Start Date | 24 / 10 / 2026 |
| End Date | 25 / 10 /2026 |
| Person Assigned | Project Manger |
| Priority | Medium |
| Resources Needed | Risk Register |
| Estimated Time | 2 Days |
| Actual Time | Not Stated |
| Predecessors | 2 |
| Slack | 1 Days |

| Name | Stakeholder Interviews |
| --- | --- |
| ID | 5 |
| Start Date | 27 / 10 / 2026 |
| End Date | 31 / 10 /2026 |
| Person Assigned | Business Analyst |
| Priority | High |
| Resources Needed | Interview Guide |
| Estimated Time | 5 Days |
| Actual Time | Not Stated |
| Predecessors | 3 , 4 |
| Slack | 0 Days |

| Name | User Questionnaire |
| --- | --- |
| ID | 6 |
| Start Date | 27 / 10 / 2026 |
| End Date | 30 / 10 /2026 |
| Person Assigned | Business Analyst |
| Priority | Medium |
| Resources Needed | Survey Tool |
| Estimated Time | 4 Days |
| Actual Time | Not Stated |
| Predecessors | 3 |
| Slack | 1 Days |

| Name | Use Casr & Requirements |
| --- | --- |
| ID | 7 |
| Start Date | 01 / 11 / 2026 |
| End Date | 04 / 11 /2026 |
| Person Assigned | System Analyst |
| Priority | High |
| Resources Needed | UML Modelling Tool |
| Estimated Time | 4 Days |
| Actual Time | Not Stated |
| Predecessors | 5 , 6 |
| Slack | 0 Days |

| Name | Data Flow Diagram |
| --- | --- |
| ID | 8 |
| Start Date | 05 / 11 / 2026 |
| End Date | 08 / 11 /2026 |
| Person Assigned | System Analyst |
| Priority | High |
| Resources Needed | Diagraming Tool |
| Estimated Time | 2 Days |
| Actual Time | Not Stated |
| Predecessors | 7 |
| Slack | 5 Days |

| Name | ER Diagram |
| --- | --- |
| ID | 9 |
| Start Date | 05 / 11 / 2026 |
| End Date | 08 / 11 /2026 |
| Person Assigned | Database Designer |
| Priority | High |
| Resources Needed | ER Modelling Tool |
| Estimated Time | 4 Days |
| Actual Time | Not Stated |
| Predecessors | 7 |
| Slack | 0 Days |

| Name | Process Specification |
| --- | --- |
| ID | 10 |
| Start Date | 09 / 11 / 2026 |
| End Date | 11 / 11 /2026 |
| Person Assigned | System Analyst |
| Priority | Low |
| Resources Needed | Documentation Tool |
| Estimated Time | 3 Days |
| Actual Time | Not Stated |
| Predecessors | 8 |
| Slack | 26 Days |

| Name | Database Design |
| --- | --- |
| ID | 11 |
| Start Date | 09 / 11 / 2026 |
| End Date | 13 / 11 /2026 |
| Person Assigned | Database Designer |
| Priority | High |
| Resources Needed | MySQL Server |
| Estimated Time | 5 Days |
| Actual Time | Not Stated |
| Predecessors | 9 |
| Slack | 0 Days |

| Name | UI Wireframes |
| --- | --- |
| ID | 12 |
| Start Date | 05 / 11 / 2026 |
| End Date | 09 / 11 /2026 |
| Person Assigned | UI / UX Designer |
| Priority | Medium |
| Resources Needed | Figma |
| Estimated Time | 5 Days |
| Actual Time | Not Stated |
| Predecessors | 7 |
| Slack | 4 Days |

| Name | Booking Module |
| --- | --- |
| ID | 13 |
| Start Date | 14 / 11 / 2026 |
| End Date | 23 / 11 /2026 |
| Person Assigned | Backend Developer |
| Priority | High |
| Resources Needed | IDE & DEV Server |
| Estimated Time | 10 Days |
| Actual Time | Not Stated |
| Predecessors | 8 , 11 , 12 |
| Slack | 0 Days |

| Name | Auth & Admin Module |
| --- | --- |
| ID | 14 |
| Start Date | 14 / 11 / 2026 |
| End Date | 19 / 11 /2026 |
| Person Assigned | Backend Developer |
| Priority | Medium |
| Resources Needed | IDE & Auth Library |
| Estimated Time | 6 Days |
| Actual Time | Not Stated |
| Predecessors | 11 |
| Slack | 8 Days |

| Name | Email Remiders |
| --- | --- |
| ID | 15 |
| Start Date | 24 / 11 / 2026 |
| End Date | 27 / 11 /2026 |
| Person Assigned | Backend Developer |
| Priority | Low |
| Resources Needed | STMP Mail Service |
| Estimated Time | 4 Days |
| Actual Time | Not Stated |
| Predecessors | 13 |
| Slack | 0 Days |

| Name | System Testing |
| --- | --- |
| ID | 16 |
| Start Date | 28 / 11 / 2026 |
| End Date | 04 / 12 /2026 |
| Person Assigned | QA Engineer |
| Priority | High |
| Resources Needed | Test Cases |
| Estimated Time | 7 Days |
| Actual Time | Not Stated |
| Predecessors | 13 , 14 , 15 |
| Slack | 0 Days |

| Name | Deployment & Training |
| --- | --- |
| ID | 17 |
| Start Date | 05 / 12 / 2026 |
| End Date | 07 / 12 /2026 |
| Person Assigned | DevOps Engineer |
| Priority | Medium |
| Resources Needed | Hosting & User Guide |
| Estimated Time | 3 Days |
| Actual Time | Not Stated |
| Predecessors | 16 |
| Slack | 0 Days |

Pert Chart

Gantt Chart